## Sheet1
Week | Task | Status | Notes | # TimerService v1 – Planning Checklist
Week 1 | Extract framework to private GitHub repo | Done
Week 1 | Add framework as submodule to app | Done |  | ## 🎯 Design Goals
Week 1 | Ensure app builds with submodule | Done
Week 1 | Invert control: app initializes framework | Done |  | - [x] Support **Time-of-Day (TOD)** scheduling
Week 1 | Implement EventManager (subscribe + publish) | Done |  | - [x] Allow **specific days of the week** (e.g., Mon/Wed/Fri)
Week 1 | Refactor file names (.hpp → .h, camelCase → snake_case) | Done |  | - [x] Handle **start/stop event pairs** with a defined duration
Week 1 | Fix: lwip_close issues, chunking bug, multipart handling | Partial | lwip_close done | - [x] Support **restart-aware delayed triggering** (catch-up on missed jobs)
Week 1 | Create minimal working app (logging + HTTP) | Done |  | - [x] Provide **both one-shot and recurring** scheduling equally
Week 2 | Finalize Logger and DebugTrace | Done | But need implmeneting in framework | - [x] Prefer **event posting** over callback execution
Week 2 | Implement Scheduler (TOD + jobs) | Done | Needs integrating, test in sprinkler | - [x] Leave **job naming/context to the application**
Week 2 | Integrate Scheduler with EventManager | Done |  | - [x] Leave **persistence optional** (not implemented in v1)
Week 2 | Add JsonService for object serialization | Done |  | - [x] Keep the service **decoupled from EventManager** (no subscribing)
Week 2 | Implement StorageManager with JSON key/value store | Done | But not settings
Week 2 | Add sample config object (e.g., timezone) | ???? |  | ## 📦 API Concepts
Week 2 | Create /config route for updates + reload | ????
Week 2 | Improve multipart and chunked body handling | Planned | Need to revisit at some point | - [ ] `scheduleDailyAt(TimeOfDay, DaysOfWeek, EventType)`
Week 3 | Implement HTTP client (GET + POST) | Planned |  | - [ ] `scheduleOneShot(time_t unixTime, EventType)`
Week 3 | Finalize AONClock (RP2040 + RP2350) | Planned |  | - [ ] `scheduleInterval(uint32_t intervalMs, EventType)`
Week 3 | Add SystemInfoService (heap, uptime, version) | Planned |  | - [ ] `scheduleDuration(TimeOfDay, durationMs, startEvent, stopEvent)`
- [ ] `triggerMissedEvents(time_t now)` ← called at boot to catch missed jobs
Week 3 | Create /status endpoint with system snapshot | ????
Week 4 | Freeze public API (minimal breaking changes) | Planned |  | ## 📚 Internal Concepts
Week 4 | Add examples: Configurable HTTP responder, Web dashboard | Planned
Week 4 | Polish middleware, routes, request/response helpers | Planned |  | - [ ] `TimeOfDay` struct with comparison and conversion helpers
Week 4 | Create README.md, LICENSE, TODO.md, ROADMAP.md | Planned |  | - [ ] `DaysOfWeek` bitmask (Sunday–Saturday)
Week 4 | Tag v0.1.0 release | Planned |  | - [ ] Internal FreeRTOS one-shot timers used for all scheduling
Week 4 | Decide on public launch vs soft release | Planned |  | - [ ] Self-rescheduling for recurring timers (e.g., daily jobs)
- [ ] Events posted using `EventManager::instance().postEvent(...)`
- [ ] Application may call `cancelJob(handle)` if job handles are exposed
## 🚫 Out of Scope (for v1)
Outplan for V1
- [ ] Named jobs or job IDs
Week 3 | Add LEDManager for SK6812 mini-E [POSTPONED] | Planned |  | - [ ] JSON persistence or config file parsing
- [ ] Job scheduler/CLI layer
- [ ] Calendar/recurrence rules beyond day-of-week
## HTTP Server Review & Suggestions
### General Strengths
- **Modular Design:** Clear separation between request, response, and server logic.
- **Embedded Considerations:** Uses static allocation, lwIP, and memory-aware design.
- **Diagnostics:** Extensive use of debug output and trace macros.
- **Multipart Handling:** Integrated with MultipartParser.
- **Cookie + Auth Support:** Cookie parsing, JWT header support.
- **Template Rendering:** Lightweight context substitution.
---
### File-by-File Feedback
#### `HttpRequest.cpp`
**Robustness**
- `receiveData()` should retry on `EINTR` or temporary socket errors.
- Better handling for malformed HTTP requests (currently returns an empty request silently).
**Efficiency**
- `getCookies()` and `getFormParams()` re-parse on every call. Cache parsed results.
**Readability**
- Parameters like `reqMethod`, `reqPath` can be renamed to `method`, `path` since the context is clear.
---
#### `HttpResponse.cpp`
**Correctness**
- Warn or assert when overwriting common headers like `Content-Length` or `Connection`.
**Chunking**
- If chunked encoding is added, `finish()` should finalize with `"0\r\n\r\n"`.
**Trace Macros**
- Use `TRACE_RESPONSE_ON` instead of one global `TRACE_ON` macro to allow module-specific tracing.
---
#### `HttpServer.cpp`
**Client Handling**
- Currently single-threaded: simple and RAM-efficient. Good for MVP.
#NAME?
- The `clientSocket > 1000` warning is clever but may need adjustment based on platform behavior.
**Error Handling**
- If `Request::receive()` fails, `handleClient()` should exit early and avoid further processing.
| --- |  |  | Request Class (formerly HttpRequest)
| ### Testing Plan |  |  | Holds:
| #### Unit Tests |  |  | TcpConnectionSocket& socket (injected)
1. **HttpRequest**
| - Header parsing |  |  | std::string method
- Cookie parsing
| - Query and form param decoding |  |  | std::string url
2. **HttpResponse**
| - Header and cookie building |  |  | std::string path
- `send()`, `start()`, `writeChunk()` functionality
| - Template rendering |  |  | std::string rawHeaderData
3. **HttpServer**
| - `initNetwork()` behavior (stub `netif`) |  |  | maybe std::string body (optional cache)
- `initServerSocket()` socket options
| - `handleClient()` with mocked request |  |  | Lazily populates from:
| #### End-to-End Tests |  |  | HttpParser (for headers, query params, cookies, form data)
- Use a mock or stub router to handle routes.
| - Simulate request via socket pair or loopback. |  |  | MultipartParser (only if needed)
- Test full route handling, including multipart, cookie, and query parsing.
---
🔍 HttpParser (new)
### Next Steps
| Let ChatGPT know whether to start with: |  |  | Static utility class with:
- Unit test scaffolding (Unity or lightweight custom framework)
| #NAME? |  |  | parseHeaders(raw) → std::unordered_map
#NAME?
parseQuery(url) → std::unordered_map
Happy to generate unit test files or test runners next!
parseCookies(headerMap) → std::unordered_map
| Class | Role |  | parseForm(body) → std::unordered_map
| Request | Parses itself from socket; owns headers/query/cookies
| Response | Writes to TcpConnectionSocket |  | Keeps parsing logic separate and testable.
| TcpConnectionSocket | Wraps networking
| Router | Routes Request to handler
| HttpServer | Accepts socket, builds Request, passes to Router
| (Optional) MultipartParser | Only used inside Request, maybe injected later |  | 🤝 MultipartParser (existing or refactored)
Injected into Request if needed.
Keeps its current structure, maybe abstract IMultipartParser if mocking is needed.
🧪 Testing
You can mock TcpConnectionSocket directly to test Request.
You can unit test HttpParser independently (pure functions).
Keeps Request free of parsing code clutter.